## Task Checklist
PROJECT TASK DELIVERABLE TRACKER
Detailed Task Plan & Completion Checklist (Mark Yes / No)
Total Tasks: | 15 | Completed (Yes): | 0 | Progress Rate: | 0%
Date | Task ID | Responsibility | Expected Deliverable | Assignee | Completed? (Yes / No) | Remarks / Notes
03-Sep | TB-L01 | Understand complete business requirement | Requirement Notes | Keerti C | No
03-Sep | TB-L02 | Discuss requirement with team | Discussion Notes | Sanjana M | No
03-Sep | TB-L03 | Break project into tasks and assign to members | Task Allocation | Abdussamad | No
03-Sep | TB-L04 | Track dataset understanding and data quality activities | Progress Update | Aditya K | No
04-Sep | TB-L05 | Coordinate data cleaning and EDA activities | Progress Update | Aditya K | No
04-Sep | TB-L06 | Review data cleaning/preprocessing work | Review Notes | Sanjana M | No
04-Sep | TB-L07 | Coordinate EDA output with ML developers | Integration Check | Keerti C | No | Got difficulty to understand EDA
04-Sep | TB-L08 | Identify and report blockers | Blocker Report | Abdussamad | No
05-Sep | TB-L09 | Coordinate KNN development | Model Progress | Namrata D | No | Got difficulty to understand mathematical tem
05-Sep | TB-L10 | Coordinate Decision Tree development | Model Progress | Abdussamad | No | Got difficulty to understand mathematical tem
05-Sep | TB-L11 | Review model evaluation and comparison | Model Review | Abdussamad | No
05-Sep | TB-L12 | Verify completion of all assigned tasks | Completion Checklist | Abdussamad | No
05-Sep | TB-L13 | Coordinate documentation and final presentation | Final Documentation | Aditya K,Namrata D | No
05-Sep | TB-L14 | Conduct team review and prepare final demo | Team Demo | All | No
05-Sep | TB-L15 | Submit final Team EOD/Project Summary | Final Summary | Abdussamad | No